## toDo
Task Unique ID | Type | Priority [0 - done; 1 - low; 5 -highest] | Entry date | Last update | Progress [%] | Target version | Delivery version | Assigned To | Issue | Task description
1 | R | 2 |  | 2019-08-11 | 10 | 0.3 |  | FOE | Duke dataset | Check Duke images set to check whether they are useful to test the segmentation algorithm.
2 | R | 5 |  | 2019-08-11 | 0 |  |  | RM | Labelled dataset | Generate a dataset of manually segmented images to support developing and validation of segmentation algorithms
3 | F | 5 |  | 2019-08-11 | 90 | 0.1 | 0.1 | ACA, FOE | Flatenning | Flatenning operation. Pending validation (e.g. compare manually labelled RPE against a flat line, and quantify)
4 | F | 5 |  | 2019-08-11 | 80 | 0.1 | 0.1 | ACA, FOE | Mosaicing / Stitching | Pending validation (e.g. compare manually labelled RPE against a flat line, and quantify)
5 | F | 5 |  | 2019-08-11 | 30 | 0.1 | 0.1 | ACA, FOE | Automatic segmentation | Automatic segmentation
6 | F | 5 |  | 2019-08-11 | 30 | 0.1 | 0.1 | ACA, FOE | Manual Segmentation | Manual editing of segmentation
7 | F | 0 |  | 2019-08-11 | 100 | 0.1 | 0.1 | ACA, FOE | Perfilometry
8 | F | 5 |  | 2019-08-11 | 50 | 0.1 | 0.2 | ACA, FOE | Layer thickness measurement | Initial algorithm ready
9 | F | 4 |  | 2019-08-11 | 30 | 0.1 | 0.2 | ACA, FOE | GUI | Development of the GUI
10 | C | 0 |  | 2019-08-11 | 0 | 0.5 |  | FOE | OpenCV dependency | Attend dependency on OpenCV (remove dependency on panorama for stitching?)
11 | C | 0 |  | 2019-08-11 | 0 | 0.5 |  | FOE | Mosaicing / Stitching | Panorama Stitching operation works only 2 images at a time. One may still join as many images as desired, but it will have to be done in pairs. For instance, if 3 images have to be stitched; you will have to make first 2, and then to the result add the 3rd. Although this works, but it is not a desirable situation. Note however that this is not a bug but a limitation of panorama itself. See summary section Adrian Rosebrock's (creator of python's panorama code) article: https://www.pyimagesearch.com/2016/01/11/opencv-panorama-stitching/ Ideally, we want to select all files at once and "solve" the whole mosaic in one go.
12 | F | 0 |  | 2019-08-11 | 100 | 0.3 |  | FOE | Scan navigation panel | Add a scan navigation panel to the GUI
13 | B | 2 |  | 2019-08-11 | 20 | 0.3 |  | FOE | Navigation panel thumbnails | Although loading of scans is correct but rendering of the thumbnails is not.
14 | D | 1 |  | 2019-08-11 | 0 | 0.4 |  | FOE | Data Model | Update documentation in Eclipse for architecture (following the separation of foundational classes).
15 | C | 5 |  | 2019-08-11 | 70 | 0.3 |  | FOE | Resize perfilometer | Perfilometer axis should resize with main scan axis
16 | C | 3 |  | 2019-08-11 | 0 | 0.4 |  | FOE | Manual Segmentation | Improving manual edition of segmentation borders.
17 | C | 3 |  | 2019-08-11 | 30 | 0.4 |  | FOE | Manual Segmentation | Incorporation of suboperation of merge ROIs. These are not aplicable to COI.
18 | C | 3 |  | 2019-08-11 | 0 | 0.4 |  | FOE | Manual Segmentation | Incorporation of suboperation of shift ROIs. These are not aplicable to COI.
19 | C | 4 |  | 2019-08-11 | 0 | 0.3 |  | FOE | GUI | Assign arbitrary colors to tissue layers.
20 | F | 3 |  | 2019-08-11 | 5 | 0.4 |  | FOE | Serialization | Serialization of the data model. See either JSON or pickle ( https://docs.python.org/3.4/library/pickle.html )
21 | C | 2 |  | 2019-08-11 | 0 | 0.4 |  | FOE | Mosaicing / Stitching | Allow selection of scan for stitching. Currently stitching is made against default selected scan.
22 | C | 3 |  | 2019-08-11 | 0 | 0.4 |  | FOE | Data Model | Provide a combined class OCTsegmentedScan that manages the raw scan and their segmentation TOGETHER seamlessly.
23 | C | 2 | 2019-11-03 | 2019-11-03 | 0 | 0.3 |  | FOE | Automatic segmentation | Detection of console/terminal or gui mode for showing a progress bar during segmentation.
24 | C | 2 | 2019-11-03 | 2019-11-03 | 0 | 0.3 |  | FOE | Automatic segmentation | Assign intratissue BG pixels to fluid.

## toDo_Codebook
Types of task
| B | Bug
| C | Code development
| D | Documentation
| F | Feature
| R | Research
Team
| ACA | Arlem Aleida Castillo \'Avila
| FOE | Felipe Orihuela-Espina
| PHW | Patrick Heyer-Wollenberg
| JHV | Javier Herrera-Vega
| SMH | Samuel Montero Hern\'andez
| RM | Rodrigo Matsui